## 2014 Mitigation Actions Update
Jurisdiction | Completed Actions | Continuing Actions (ongoing or modify) | Deleted Actions
Adel | 3 | 10 | 1
Completed Actions (Include 2014 Action ID) | Completion Date | Cost | Funding Source | Partners | Office Responsible | Obstacles to Implementation
Adel 1 | 2016-10-01 | 638564 | Capital Improvement Program | ISWEP | Public Works | Funding & Policy
Deleted Actions (Include 2014 Action ID) | Reason for Deletion
Adel 1: Implement a stormwater utility to maintain drainage infrastructure. | No political support at this time.
Continuing Actions (Include 2014 Action ID) | Progress Towards Completion | Timeline for Completion
Adel 4 | Funding secured; construction to being in Spring 2019 | 1 year

## 2019 Mitigation Actions
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Update tornado warning system | Tornado | Both | Hazard Mitigation Plan | In Progress / Continue | Update has been done but Adel would like to add new sirens | 4 |  |  | Funding | Mayor/City Council | Iowa Homeland Security and Emergency Management; Polk County Emergency Management | HMGP 5% | TBD | Improve the City's ability to provide outdoor warning of severe weather, enabling residents to take life- saving action. | 5 years

## Alleman
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construct retention pond at Northeast 134 | Flash Flooding | Existing | Capital Improvement Plan | Not Started / Continue | Plan to continue development would need retention pond. However, development plans have been tabled. This project is still a good idea if additional development occurs. | 4 |  |  | Funding | Mayor/City Council | Iowa Homeland Security and Emergency Management; Iowa Department of Natural Resources | HMGP, FMA, PDM, General Fund | TBD | Reduce damages to existing structures as well as prevent damage to future structures that may be constructed in area slated for potential development | 10 years
| Consider participation in the NFIP | River Flooding | Both | Hazard Mitigation Plan - floodplain management ordinance if adopted | New |  | 2 |  |  | Staff Time | Mayor/City Council | Iowa Department of Natural Resources | No funding necessary | N/A | Allow owners of existing structures to purchase flood insurance, offsetting any flood damage to structures as well as provide a mechanism for the City to regulate any future development in designated floodplains | 2 years

## Altoona
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue |  | 2 |  |  | None Identified | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Flooding, infrastructure damage, property damage, erosion | Ongoing

## Ankeny
Action ID | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score | Priority | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
(MPO Only) | [7 empty] | (MPO Only) | (MPO Only)
| Construct safe room(s) at Autumn Ridge Mobile Home Park | Tornado | New | Hazard Mitigation Plan | Not Started / Continue | Private residential mobile home facility currently without safe room(s) | 4 |  |  | Lack of funding, Space and Authority | City Manager's Office | Autumn Ridge Ownership | PDM, HMGP | TBD by engineer | Personal loss to residents and other occupants from tornado / wind dangers | 4 Years
| Sanitary sewer capacity improvements southeast area relief sewer | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue | Last phase of multi-year project is scheduled to be completed. | 4 |  |  | Construction difficulties | Public Works | None | HMGP | $100,000 (remaining work) | Property damage to residents | 1 Year
| Sanitary sewer capacity improvements Southeast 2nd Avenue trunk interconnect | Flash Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Construction difficulties | Public Works | None | PDM, HMGP | 250000 | Property damage to residents | 1 Year
| Sanitary sewer capacity improvements West Outfall Relief sewer | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue | Project included in capital improvements program. Project is being designed at this time. | 4 |  |  | Construction difficulties, Property acquisition | Public Works | None | Sewer Enterprise Funds | $1.79 Million | Property damage to residents due to sanitary sewer backups | 1 Year
| Storm sewer/channel improvements Southeast 4th Street and Wanda storm sewer | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue | The majority of this project is completed. The last phase will be constructed in 2014/2015. | 4 |  |  | Construction difficulties, Property acquisition | Public Works | None | Stormwater Enterprise Funds | $175,500 remaining | Property damage and erosion damage avoided | 1 Year
| Storm sewer/channel improvements Tributary "A" Stream and Southeast Tributary to Four Mile Creek channel improvements | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue | This project is approximately 50% completed at this time. | 4 |  |  | Construction difficulties, Property acquisition | Public Works / Municipal Utilities | None | Stormwater Enterprise Funds | $1.9 Million | Additional property damage and erosion damage avoided | 2 Years
| Storm sewer/channel improvements Four Mile Creek bank stabilization | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue | This project is approximately 30% completed at this time. | 4 |  |  | Construction difficulties, Property acquisition | Public Works / Municipal Utilities | None | PDM, HMGP | 250000 | Additional property damage and erosion damage avoided | 3 Years
| Reconstruct storm water detention - Packard Pond improvements | Flash Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue | No project schedule at this time. | 4 |  |  | Property acquisition, Deep Trench excavation | Public Works | Private Resident | PDM, HMGP | 200000 | Downstream flooding and stream erosion | 4 Years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing | NFIP Floodplain Management Program | In Progress / Continue | Participating in multi- jurisdictional Fourmile Creek Study. Assisting with providing floodway info for Firm map replacements. | 2 |  |  | Multi-agency funding required, Property acquisition | City Manager's Office | IDNR, FEMA | Existing Resources | N/A | Flooding, infrastructure damage, property damage, erosion | Ongoing
| Storm sewer / channel improvements - West First Street Storm Sewer Improvements | Flash Flooding | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Construction difficulties, Property acquisition | Public Works | None | Stormwater Enterprise Funds | $3.3 Million | Flooding, property damage and erosion damage avoided | 4 Years
| Embankment stabilization - NW Irvinedale Drive | Sinkholes/Land slide | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Construction difficulties, Earth stabilization issues | Public Works | None | Stormwater Enterprise Funds, PDM, HMGP | 250000 | Flooding, property damage and erosion damage avoided | 4 Years
| Reconstruct storm water detention - Wildflower Public Pond improvements | Flash Flooding | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Construction difficulties, Access to site | Public Works | None | PDM, HMGP | 275000 | Residential flooding, downstream flooding and erosion | 4 Years
| Storm sewer/channel improvements - SE Creekview Drive Improvements | Flash Flooding | Existing | Capital Improvements Program | NEW |  | 4 |  |  | Construction access, Maintaining access | Public Works | None | Stormwater Enterprise Funds, PDM, HMGP | $1.8 Million | Flooding of commercial and industrial businesses avoided | 4 Years
| Construct safe room(s) at On With Life Care Facility | Tornado | New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Lack of funding, Space and authority | City Manager's Office | Private Care Provider | PDM, HMGP | TBD by Engineer | Personal loss to facility residents from tornado / wind dangers | 4 Years

## Ankeny Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Multi-purpose Safe Rooms District Wide | Tornado | Both | Hazard Mitigation Plan | NEW |  | 4 |  |  | Cost | Safety Manager | None Identified | PDM, HMGP | TBD by engineer | Life/Survivability | 6 Years
| Safety Glass | Tornado | Both | Hazard Mitigation Plan | NEW |  | 4 |  |  | Cost | Safety Manager | None Identified | PDM, HMGP | 120000 | Life/Property | 2 Years
| Back-up Facility Generators | Tornado | Both | Hazard Mitigation Plan | NEW |  | 4 |  |  | Cost | Safety Manager | None Identified | PDM, HMGP | TBD by engineer | Network Systems/Vital Data | 4 Years

## Bondurant-Farrar Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Purchase NOAA Emergency Radios for Morris elementary and the other three buildings, totaling 10. | Tornado | Existing and New | Hazard Mitigation Plan | NEW | Starting this action Spring of 2014 | 4 |  |  | NA | School Board | School Foundation | Existing Resources | $400-$500 | Advanced warning for life threatening situations | 1 Year

## Bondurant
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Generator at public safety building | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue | Scheduled for Summer 2014 | 4 |  |  | None | City Administrator | Polk County | Local Tax Levy | 3000 | Allows for continued operations during power outages. | 6 months
| Generator for City Hall phones | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue | Scheduled for Summer 2014 | 4 |  |  | None Identified | City Administrator | None Identified | Local Tax Levy | 3000 | Allows for continued operations during power outages. | 6 months
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain \mgt. program | Not Started / Continue | Scheduled for September 2014 | 1 |  |  | None Identified | City Administrator | IDNR, FEMA | Existing Resources | N/A | regulatory, prevents flooding and property loss | Ongoing

## Clive
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construction of three regional storm water detention facilities at: 100 Street and Indian Hills; 156th Street and Hickman Road; Douglas Road and Berkshire Road | River Flooding | New | Hazard Mitigation Plan | In Progress / Continue | 100th Street - 0% Complete/156th Street - 100% Complete/Douglas Road - 100% Complete | 4 |  |  | Funding | City Administrator | N/A | General Funds/Storm Water Fund, HMGP, PDM, FMA | $250,000- $500,000 | Storm water runoff damage, downstream flooding | 3-5 Years for remaining facility
| Acquisition of property along Walnut Creek as well as Little Walnut Creek to reduce repetitive loss potential | River Flooding | N/A | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Funding | City Administrator | N/A | General Funds/Storm Water Fund, HMGP, PDM, FMA, RFC, SRL | $1 million | Storm water runoff damage | Ongoing
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue |  | 4 |  |  | N/A | Floodplain Manager | FEMA, State | Existing Resources | N/A | Reduce loss of life and property due to flooding. | Ongoing
| Purchase and installation of an emergency backup generator at the Police and City Hall/Administration Building | River Flooding | New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | City Administrator | FEMA, State | FEMA, General Fund | 100000 | Capability to manage and respond to emergency situations. | 2 Years
| Outdoor Warning Siren replacement | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | Fire Department | FEMA, State | FEMA, General Fund | 15000 | Advance warning to community | 3 Years
| Outdoor Warning Siren addition | Tornado | New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | Fire Department | FEMA, State | FEMA, General Fund | 25000 | Advance warning to community | 4-5 Years
| Replace (2) flap gates with back flow systems on Swanson Blvd | River Flooding | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | Public Works | FEMA, State | FEMA, General Fund | 100000 | Prevent flooding | 2 Years
| Stream bank stabilization along Walnut Creek | River Flooding | New | Hazard Mitigation Plan Walnut Creek Stabilization Study | NEW |  | 4 |  |  | Funding | Community Development | Corps of Engineers, DNR | FEMA, General Fund, Strom Water Utility Fund, State Grants | 3700000 | 25,000 feet of unstable bank | 3-5 Years

## DCG Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construction of saferooms in existing or new school buildings | Tornado | Existing and New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | School Board | Iowa Homeland Security and Emergency Management, FEMA | LOST (Local Option Sales Tax), PPEL (Voted Equipment Levy), HMGP, PDM | $1 Million to $2 Million (TBD) | Life Safety | Ongoing

## Des Moines
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Remove mitigated properties from repetitive loss property list | River Flooding | N/A | Hazard Mitigation Plan | In Progress / Continue | Handled with participation in the NFIP Community Rating System on an annual basis. | 1 |  |  | Inter- departmental communication | Community Development Department | Engineering Department | Existing Staff Resources | TBD by Engineer | Lower insurance premiums | 1 Year
| Pursue remedial flood mitigation actions associated with the Southeast Des Moines (SEDM) Levee, US 65 | River Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Land acquisition, Permitting, Funding | Public Works Department | IDOT, USACE | PDM, HMGP | TBD | Impacts levee certification for SE Des Moines Levee which protects portions of Des Moines and Pleasant Hill including the Wastewater Reclamation Facility. | TBD
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue | Continued enrollment in the NFIP along with CRS program as a 7 rating | 2 |  |  | None Identified | Community Development Department | Engineering Department | Existing Resources | N/A | Availability of Flood Insurance to residents and businesses in the City and proactive management of any future development in floodplain areas to minimize risk. | Ongoing
| Construct safe room(s) at Des Moines Municipal Housing Agency's multi-family units | Windstorms | Existing and New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Space constraints | Housing Service Department | Engineering Department | City General Operating Fund / Disposition Proceeds | TBD | Reduce injuries and property damage | TBD
| Harden single family home scattered site Public Housing units | Windstorms | Existing and New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Space constraints | Housing Service Department | Engineering Department | City General Operating Fund / Disposition Proceeds | TBD | Reduce injuries and property damage | TBD
| Treatment and removal of ash trees in response to onset of Emerald Ash Borer (EAB) | Animal/Crop/Pla nt Disease | Existing | EAB Mitigation Plan | NEW | Removal began in 2010 & will continue through 2025 | 4 |  |  | EAB insect not yet discovered in the city. Cost of treatment and removal. Logistics of treating 5800 and removing 7200. | Public Works Department | MidAmerican Energy Corp. and Tree Des Moines TreeKeepers | City General Operating Fund, Storm Water Utility Fund | $9.6 million | Avoid excess rainfall runoff | 11 Years
| Des Moines River Flood Mitigation Improvements - Flood protection system improvements (levees, floodwalls, pump stations, etc.) to maintain FEMA accreditation despite increased flows identified in 2011 Des Moines River Regulated Flow Frequency Study. | River Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | USACE permitting, Funding | Public Works Department | USACE | Stormwater Utility, USACE, Iowa Flood Mitigation Program | $20 million | Impacts FEMA accreditation of three City of Des Moines operated Corps of Engineer levees that protect the downtown area. | 5 Years
| Hamilton Drainage Area Stormwater Improvements - Storm sewer conveyance improvements on Shawnee Avenue from 11th Street to 7th Street, and also storm sewer improvements from Shawnee Avenue and Columbia Street to Wright Street and Euclid Avenue to replace a deteriorating wooden box storm sewer. | Flash Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | Public Works Department | None Identified | Stormwater Utility | $12 million | Improvements to be designed to reduce risk of property damage due to flash flooding up to the 1% annual chance flood event | 6 Years
| Leetown Creekway Stormwater Improvements - Increased storm sewer capacity between University Avenue and Dean Avenue and channel improvements from south of Dean Avenue to confluence with Fourmile Creek. | Flash Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | Public Works Department | None Identified | Stormwater Utility | $9.5 million | Improvements to be designed to reduce risk of property damage due to flash flooding up to the 1% annual chance flood event | 5 Years
| Closes Creek Stormwater Improvements - Replace Culverts @ 30th Street and Jefferson Avenue. Storm sewer improvements along Maquoketa Drive. | Flash Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | Public Works Department | None Identified | Stormwater Utility | $5 million | Improvements to be designed to reduce risk of property damage due to flash flooding up to the 1% annual chance | 5 Years
| Remove repetitive loss properties from flood prone areas | River Flooding | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Owner resistance, Funding | Engineering Department | Community Development Department | HMGP, CDBG, Local funds, State funds | $5 million | Reduce injuries and property damage | 10 Years

## DSM Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construct new gymnasium as a safe room- Moore Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 1.5 Years
| Construct a multipurpose room as a safe room- Cowles Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding |  | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 years
| Construct a multipurpose room as a safe room- Findley Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room- Howe Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room-Jackson Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room-Jefferson Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room-Lovejoy Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room-Madison Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room-Studebaker Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years
| Construct a multipurpose room as a safe room-Wright Elementary | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | Iowa Homeland Security and Emergency Management Division, FEMA | Operations Department | HMGP, PDM, PPEL, SWP | TBD by engineer | Life Safety of students and staff sheltered in saferoom areas | 5 Years

## DMWW
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Upgrade Interior Drainage Pumping System inside the levee protected area at Fleur Drive Water Treatment Plant | Flash Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | DMWW Engineering Department | N/A | CIP | 250000 | Areas inside the ring levee flood during rain events when levee gates and storm water valves are closed. These improvements would prevent interior flooding. | 2 Years
| Relocate grounds maintenance facility to the dry side of the levee system to reduce repetitive loss potential | River Flooding | New | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | DMWW Engineering Department | N/A | CIP | 1000000 | Recurrent property damage when existing grounds maintenance facility floods. | 2 Years
| Evaluate and repair flood gates located at the Fleur Drive Water Treatment Plant | River Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | DMWW Engineering Department | N/A | CIP | TBD by engineer | Flooding of the treatment plant due to leakage at levee gate. | 1 Year
| Evaluation of ring levee protecting Fleur Drive Water Treatment Plant | River Flooding | Existing | Capital Improvement Plan | NEW |  | 4 |  |  | None Identified | DMWW Engineering Department | N/A | Operating Budget | 200000 | Flooding due to leakage through or under levee. | 1 Year

## Elkhart
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construct safe room at Elkhart Memorial Park | Windstorms | New | Hazard Mitigation Plan | Not Started / Continue | NO BUILDING TO HAVE ONE YET | 4 |  |  | Need new building | Mayor | Community | PDM, HMGP, Community donations | TBD by Engineer | Safety of residents | 5 Years
| Construct safe room in NEW fire station | Windstorms | New | Capital Improvement Plan | Not Started / Continue | Plan to include in new station when built | 4 |  |  | Looking for suitable location | Mayor | Fire Grants, Community | PDM, HMGP, Grants, Community Donations | >$250,000 | Place of safety in case of storms | 5 Years
| Generator for new fire station | Windstorms | New | Hazard Mitigation Plan | Not Started / Continue | Plan for one in NEW Fire Station | 4 |  |  | Cost | Mayor | Community | HMGP 5%, City funds, Donations | <$250,000 | Safe room heat in Winter | 5 Years
| Generator at city water plant | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue | Have a rental unit available if needed | 4 |  |  | Cost | Mayor | Community | HMGP 5%, Community funds | <$250,000 | Loss of water source for fires | 2 Years
| Construct safe room at Elkhart Community Center | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue | Plan to add on or construct new building | 4 |  |  | Cost | Mayor | Community | PDM, HMGP | TBD by Engineer | Place of safety in case of storms | 5 Years

## Grimes
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construct safe room at sports complex | Windstorms | New | Hazard Mitigation Plan | Not Started / Continue |  | 1 |  |  | Cost | City Administration | Possibly one of the ball leagues | PDM, HMGP | TBD by Engineer | Injury or death of park attendees unable to find shelter | 3 Years
| Generators at City Hall | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 2 |  |  | Costs | City Administration | None | HMGP 5% | <$250,000 | City services being interrupted | 3 Years
| Generator at fire station | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 2 |  |  | Costs | City Administration | None | HMGP 5% | <$250,000 | Delay in emergency response, freeze damage to equipment | 3 Years
| Warning siren northeast and southwest areas of city | Windstorms | New | Hazard Mitigation Plan | Not Started / Continue |  | 1 |  |  | Securing property and power supply | City Administration | None | HMGP 5% | <$250,000 | Providing residents advanced warning of an approaching storm | 18 months
| Elevate bridge on North James Street, north of wastewater treatment plant | River Flooding | Existing | Capital Improvement Plan | In Progress / Continue | This has been added to the long term plans within the CIP | 1 |  |  | Right of way acquisition | City Administration | DOT | Capital Improvement, HMGP | 500000 | Emergency access to homes & school. Reduced flooding | 5 Years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue |  | 2 |  |  | None Identified | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Regulation of future construction in floodplain areas and availability of flood insurance in City limits | Ongoing

## Johnston
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Improve communications to include list serve, mass telephone communications, and radio cable | Windstorms | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 1 |  |  | None | Public Safety Department | Media outlets | Existing Staff Resources | <$250,000 | Provide real time notification to residents in an emergency | Ongoing
| Maintain contact with Pioneer/DuPont regarding potential hazards | Windstorms | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 1 |  |  | None | Public Safety Department | Pioneer | Existing Staff Resources | <$250,000 | Provide & receive real time notifications regarding health, safety, or security concerns. | Ongoing
| Generator at City Hall | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 2 |  |  | Costs | City Administration | None | HMGP 5% | <$250,000 | City services being interrupted | 2 Years
| Generator at fire station / police station | Windstorms | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 2 |  |  | Costs | Public Safety Department | None | HMGP 5% | <$250,000 | Delay in emergency response, freeze damage to equipment | 2 Years
| Investigate repetitive loss property mitigation options regarding recently annexed area(s) | River Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 1 |  |  | Obtaining information | Community Development | Assessor’s office & FEMA | Existing Staff Resources | <$250,000 | Helping to reduce future problems | 5 Years
| Continue to work with Iowa DOT to eliminate flooding at Northwest Beaver Drive (water impounded since the 2008 flood may be affecting the water table and may be polluted) | River Flooding | N/A | Storm Water Management Plan | In Progress / Continue |  | 4 |  |  | Inter-governmental cooperation | Community Development | DOT, Army Corp of Engineers | Existing Staff Resources, HMGP, PDM, FMA | <$250,000 | Reduce or eliminate property damage, maintain roadways lost due to flooding | 5 Years
| Conduct flood impact study on Merle Hay and Beaver Creek area | River Flooding | N/A | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Costs | Community Development | DOT, Army Corp of Engineers | PDM if it results in projects | <$250,000 | Reduce or eliminate property damage, maintain roadways lost due to flooding | 5 Years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue |  | 4 |  |  | None Identified | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Mitigate damages to new development in floodprone areas as well as allow residents and businesses to purchase flood insurance. | Ongoing

## Johnston Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construct safe room/building for outside sports complex | Tornado | New | Hazard Mitigation Plan | New |  | 4 |  |  | Funding | School Board | Iowa Homeland Security and Emergency Management | PDM, HMGP | TBD by engineer | protect students and faculty from injury or death as a result of tornado events | 4 Years
| Storm sewer improvements North of the High School to prevent flooding in athletic buildings, practice and parking | Flash Flooding | Existing | Storm Water Management Plan | New |  | 4 |  |  | Funding | School Board | City of Johnston | PDM, HMGP | TBD by engineer | Prevent flood damage to athletic buildings, practice fields and parking areas | 2 Years

## Mitchellville
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Improve ditch and culvert drainage in northwest part of town | Flash Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  |  |  | Iowa Homeland Security and Emergency Management | Bond funds, CDBG, HMGP, PDM | TBD by engineer | Prevent flooding to nearby outbuildings and basement in nearby residences | 1 Year
| Backup power generator for police/fire station | Windstorms | New | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  |  |  | Iowa Homeland Security and Emergency Management | General Funds, Blake Trust Account, HMGP 5% | 30000 | Provide backup power to police/fire critical services | 2 Years
| New roof for police/fire station | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  |  |  | None | Blake Trust Account | 5000 | Avoid additional damages to structure and contents | 1 Year
| Re-wiring the electrical system for police/fire station | Windstorms | Existing | Hazard Mitigation Plan | In Progress / Continue | Everything is complete except what feeds into the air conditioning | 4 |  |  |  |  | None | General Fund, Blake Trust Account | $3,500-$4,000 | Needs to be completed before generator can be installed | 1 Year
| New siren on east edge of town | Windstorms | New | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  |  |  | Iowa Homeland Security and Emergency Management | General Funds, HMGP 5% | 20000 | Provide advanced outdoor warning for citizens to take shelter | 1 Year
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | New |  | 4 |  |  |  |  | IDNR, FEMA | Existing Resources | N/A | Mitigate damages to new development in floodprone areas as well as allow residents and businesses to purchase flood insurance. | Ongoing

## North Polk Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Conduct Needs analysis and feasibility study for safe rooms at Central Elementary and North Polk Junior/Senior High School | Tornado | Existing | Hazard Mitigation Plan | NEW | Alleman 5 Action ID in 2009 plan | 1 |  |  | Funding | DPW/School Board | N/A | Existing Staff Resources | <$250,000 | N/A | 4 Years

## Pleasant Hill
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Generators for lift stations: 6400 Southeast 6th Street; Northeast 80th Street; Vandalia Road; Harbor Lake Drive, and Southeast 60th Street | Windstorms | Existing | Capital Improvement Plan | In Progress / Continue |  | 4 |  |  | Not all lift stations lifted are actively in use, budget & time restraints | City Public Works | City Council, City Manager | Capital Improvement Plan Funds, HMGP 5% | $40,000 per generator | Reduce physical damage to structures | 1 Year
| Flood mitigation planning elevation of southeast connector so water passes underneath – current road is in flood zone | River Flooding | New | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Time & budget restraints | City of Des Moines City Manager | City Council, City Manager, City of Des Moines | N/A, PDM if results in a fundable project | $100 million for entire project | Flooding potential is reduced and potential damage to structures is minimized | 5 Years
| Creation of storm water utility (with taxing and bonding authority) | Flash Flooding | N/A | Hazard Mitigation Plan | Not Started / Continue |  | 2 |  |  | Politically & Socially difficult to increase user fees | Newly Created Stormwater Utility Agency | Stormwater coordinator, City council, Community development | N/A | $40-50,000 | Stormwater system is kept current to avoid any losses due to flooding, backups, or other stormwater related issues | 2 to 5 Years
| Relocation of and construction of new fire station | Windstorms | New | Capital Improvement Plan | Not Started / Continue |  | 4 |  |  | Time, Budget restraints | City Fire | City Fire, City Council, Funding sources | Capital Improvement Plan Funds | TBD by engineer | More adequate services for fire employees could produce faster response times, better equipment storage, loss of life, prevention of damages | 3 Years
| Relocation of gas pumps for city vehicles which are in flood zone | River Flooding | New | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Land acquisition | Public Works | City Council | HMGP, FMA, PDM | TBD by engineer | Provide continued access to public vehicles during an emergency event | 3 Years
| Safe room incorporation into new city facilities | Windstorms | New | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | time and budget restraints | Community Development | City Council, City Staff, funding agencies | HMGP, PDM | TBD by engineer | Minimize loss of life | N/A
| Regional detention facility at northeast 80th Street | Flash Flooding | New | Future Land Use Plan, Comprehensive Plan | In Progress / Continue |  | 4 |  |  | time and budget restraints | City Public Works | Regional entities, City Council, City Manager | N/A | $4 million | reduce flooding risks and potential damage to structures | 1 Year
| Enhance combined development of Des Moines Area Regional GIS Partnership | Flash Flooding | N/A | Ongoing Project | In Progress / Continue |  | 3 |  |  | time restraints, skill capabilities & financial resources | Community Development, City of Des Moines IT | Metro Cities, Des Moines IT | City Budget, HMGP 5% | <$250,000 | Provide accurate and reliable data for emergency professionals to provide immediate and successful responses | 5 Years
| Construction of new culvert at Little Four Mile Creek Drive 4400 block | Flash Flooding | New | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | time and budget restraints | Department of Public Works | City Engineer | HMGP, FMA, PDM | 150000 | reduce flooding risks and potential damage to structures | 1 Year
| Pursue remedial flood mitigation actions associated with the South East Des Moines (SEDM) Levee, US 65 | River Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | time and budget restraints | Iowa DOT, USACE and others TBD | City Council | PDM, HMGP | TBD | reduce flooding risks and potential damage to structures | TBD
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue |  | 2 |  |  | None Identified | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Mitigate damages to new development in floodprone areas as well as allow residents and businesses to purchase flood insurance. | Ongoing

## Polk City
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Safe Room for: police department/fire department/ community center/city hall/ visitors at area lakes | Tornado | Existing | Capital Improvement Plan | Not Started / Continue |  | 4 |  |  | Funding | City Administration | None Identified | City General Fund, Safe Room Grant, HMGP, PDM | TBD by engineer | Provide refuge for life safety during tornado events | 10 Years
| Safe room for sports complex | Tornado | New | Capital Improvement Plan | Not Started / Continue |  | 4 |  |  | Funding | City Administration | None Identified | City General Fund, Safe Room Grant, HMGP, PDM | TBD by engineer | Provide refuge for life safety during tornado events | 10 Years
| Advocate for structural enhancements to Mile Long Bridge to bring to current DOT standards | River Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue | On state hwy, not responsibility of city | 2 |  |  | Not within our jurisdiction | City Administration | None Identified | Iowa DOT, US DOT | N/A | Mitigate interruption of this key access point | Ongoing
| Raise levee elevation for sewer treatment facility on East Broadway Street | River Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Funding | City Administration/ Public Works | None Identified | City | TBD by engineer | Mitigate potential flood damage to sewer treatment facility | 15 years
| Advocate for expanding pumping capacity for sewer treatment facility pumping to Saylorville Reservoir | River Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 2 |  |  | Not within our jurisdiction | City Administration/ Public Works | None Identified | N/A | N/A | Mitigate flood damages caused by sewer backup | Ongoing
| Raise wellheads and associated electrical for Polk City Well Field on North 3rd Street and East Northside Drive | River Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Funding | City Administration/ Public Works | None Identified | City | TBD by engineer | Mitigate potential damage to wellheads and electrical components from flooding | 5-10 Years
| Storm sirens at Hugg Drive and Westside Drive | Tornado | New | Hazard Mitigation Plan | NEW |  | 1 |  |  | Funding | City Administration/ Public Works | None Identified | City | TBD by engineer | Provide advance outdoor warning of severe weather to allow residents to take shelter | 5 Years
| Lining of public sewers to mitigate infiltration of the main pump. | Flash Flooding | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | City Administration/ Public Works | None Identified | City | TBD by engineer | mitigate damage to the pump as well as damages that could occur if pump is non- operational | 5 Years
| Culvert at N 3rd -Bedshed Drive to mitigate water running over the road flooding buildings | Flash Flooding | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | City Administration/ Public Works | None Identified | City | TBD by engineer | Mitigate water going over the road | 5 Years
| Join the National Flood Insurance Program | River Flooding | New Existing | Hazard Mitigation Plan | NEW |  | 2 |  |  | Staff Time | City Administration | Iowa Dept. of Natural Resources | N/A | N/A | This will enhance the City's ability to regulate development in floodplain areas as well as allow residents and businesses to purchase flood insurance | 1 Year

## Polk County
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Construction of Additional Storm Water Detention Basins and Channel Improvements to Polk County's "Hamilton Drain" Drainage District | Flash Flooding | New | Capital Improvement Plan | In Progress / Continue | Priority #1 Awarded Hazard Mitigation Funds in 2013 using $7,422,000 HMGP, $989,600 State, $1,484,400 Local Funds | 4 |  |  | None-moving forward | DPW | Iowa Homeland Security & Emergency Management, FEMA | 75% HMGP, 10% State, 15% Polk County Hamilton Drainage District Funds | $11 million | Mitigate damages caused by flooding by providing stormwater detention and channel improvements | 1 Year
| Construct Martin Luther King Parkway extension from Euclid Ave. to I-80 with new Interchange on I-35/80 | River Flooding | New | Capital Improvement Plan | In Progress / Continue | Priority #5 Still working to complete Environmental review of proposed roadway corridor. | 4 |  |  | Environmental Clearance/ STUDV/ Funding | DPW | Area Cities, Iowa DOT, Federal Highway Administration | Federal Highway STP Funds, Polk County Funds | $40 million | Mitigate flooding over road, Better traffic flow | 10 Years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue | Priority #4 | 2 |  |  | None Identified | Floodplain Manager | Area Cities | Existing Resources | N/A | Availability of Flood Insurance to residents and businesses in the City and proactive management of any future development in floodplain areas to minimize risk. | N/A
| Construction of Storm Water Detention Basins, Buffer Strips, and Channel Improvements to Fourmile Creek though the Fourmile Creek Watershed Authority | Flash Flooding | Existing and New | Watershed Authority / Management Plan | NEW | Priority #2 | 4 |  |  | Funding | DPW | 15 Watershed Authority members, including Cities, Counties, and Soil Conservation Districts. | State Grants, Local funds, HMGP | $40 million | Mitigate damages caused by flooding by providing stormwater detention and channel improvements | 10 Years
| Construction of Storm Water Detention Basins, buffer Strips, and Channel Improvements to Mud, Camp, and Spring Creek watersheds though the Watershed Authority | Flash Flooding | New | Watershed Authority / Management Plan | NEW | Priority #3 | 4 |  |  | Funding | DPW | 11 Watershed Authority members, including Cities, Counties, and Soil Conservation Districts. | State Grants, Local funds, HMGP | $25 million | Mitigate damages caused by flooding by providing stormwater detention and channel improvements | 10 Years

## Runnells
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Backup power generator for community center at 108 Brown Street | Tornado | New | Hazard Mitigation Plan | Not Started / Continue | Working on community betterment grant of Polk Co. | 4 |  |  | Funding | Mayor's Office |  | HMGP 5% | 30000 | Provide alternate power during power outages for community center which can be used during various hazard events such as extreme cold, extreme heat, etc. | 1 Year
| Document electronic backup for city critical documents | Tornado | N/A | Hazard Mitigation Plan | Not Started / Continue |  | 3 |  |  | Time constraint Funding | Mayor's Office | Summit- software programs | General Funds | TBD | Provide for continuity of government if primary documents are lost | 1 Year
| Development of new lagoon at sewer station to mitigate overflow in high rains | Flash Flooding | New | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Funding | Mayor's Office | Msa Professionals Des Moines Water Works | Sewer funds, CDBG grants | 250000 | Prevent overflow of sewage during flash flooding. This may also help prevent sewer backup in basements. | 5 years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | New |  | 2 |  |  | None Identified | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Mitigate damages to new development in floodprone areas as well as allow residents and businesses to purchase flood insurance. | Ongoing

## Southeast Polk Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Contraction of Multi-purpose Safe Rooms District Wide | Tornado | New | Capital Improvements Plan | NEW |  | 4 |  |  | Funding | Building and Grounds Department | Polk County Emergency Management | PDM, HMGP, bonds, sales tax, PPEL | $400,000 to $1,000,000 per school | Life Safety of students and staff | 2 to 10 years

## Urbandale
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Replace one warning sirens at City Hall | Tornado | New | Hazard Mitigation Plan | In Progress / Continue | In progress | 1 |  |  | Pending obtaining an easement | Fire Department | None Identified | HMGP 5% | 18000 | Improved warning | This year
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue | In Progress / Continue in Plan Update | 2 |  |  | VERY poor quality of existing FEMA maps | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Private property losses, Public infrastructure losses, and Potential injuries and deaths from periodic flooding | Ongoing
| Fire Station No. 42: Expansion of Living Quarters | Structural Fire | Existing | URB CIP# BU06-01 | NEW | This project is going out to bid in January | 2 |  |  | None Identified | Fire Department | None Identified | GOB | $11,96,500 | Enhance emergency services | In progress
| Fire Station No. 43: Construction and Satellite Police | Structural Fire | New | URB CIP# BU07-01 | NEW | This project in under study and City is exploring cost reduction opportunities. Scheduled for 2018. | 2 |  |  | None Identified | Fire Dept. and Police Dept. | Investigating opportunities | GOB / Voter approved bond | 2420000 | Enhance emergency response | 5 years
| Parks and Public Works Maintenance Facility: 94th Street / 95th Street and Hickman Road | Winter Storm | Existing | URB CIP# BU11-01 | NEW | In progress | 2 |  |  | None Identified | Dept. of Engineering and Dept. of Public Works | None Identified | TIF | 12320000 | Improved efficiencies, Response times | In progress
| Parks and Public Works Satellite Field Maintenance Facility: 170th Street and Waterford Road | Winter Storm | New | URB CIP# BU02-01 | NEW | Continue in plan | 2 |  |  | None Identified | Dept. of Engineering and Dept. of Public Works | None Identified | GOB | 2392500 | Improved efficiencies, Response times | 5 years
| Elevated bridge at 156th and Walnut Creek | Flash Flooding | Existing | URB CIP# BR02-02 | NEW | Scheduled for 2015 | 1 |  |  | Corps & DNR permitting | Dept. of Engineering and Dept. of Public Works | None Identified | Capital Improvements | $1.7 million | Damage from flooding, transportation issues | 2 Years
| Fire: Truck Replacement | Structural Fire | Existing | URB CIP# EQ12-03 | NEW | This project is planned replacement of a fire truck that will be reaching the end of useful life. | 2 |  |  | None Identified | Fire Department | None Identified | Capital Improvements | 500000 | Replace outdated equipment | 3 years
| Traffic Signal Preemption | Structural Fire | New | URB CIP# TE11-01 | NEW | This project is being developed with implementation being phased in over several years. | 2 |  |  | None Identified | Dept. of Engineering and Dept. of Public Works | None Identified | GOB | 672000 | Improved efficiencies, Response times | In progress
| 100th Street Bridge at I-35/80 | Transportation Incident | Existing | URB CIP# BR06-11 | NEW | Starting design in 2014 | 1 |  |  | FHWA Approval | Dept. of Engineering and Dept. of Public Works | State of Iowa | Federal/State and TIF | 7700000 | Improved efficiencies: Response times, Traffic flow and Evacuation routes | 2 years
| Drainage Improvements-Various Locations | Flash Flooding | Existing | URB CIP# SS02-01 | NEW | In progress | 1 |  |  | DNR permitting | Dept. of Engineering and Dept. of Public Works | None Identified | GOB/Storm Water Utility | 1250000 | Improve drainage/Creek erosion | In progress
| Oakwood Drive Channel Improvements | Flash Flooding | Existing | URB CIP# SS13-03 | NEW | In progress | 1 |  |  | Corps/DNR | Dept. of Engineering and Dept. of Public Works | None Identified | FEMA/GOB | 749000 | Property protection - public/private (homes) | In progress
| 73rd Place Storm Drainage Improvement | Flash Flooding | Existing | URB CIP# SS11-01 | NEW | In progress | 1 |  |  | None Identified | Dept. of Engineering and Dept. of Public Works | None Identified | Grants and local funds | 2760000 | Property protection - public/private (homes) | In progress
| Interchange Modifications and Collector Distributor Connections- Interstate 35/80 and Highway 141 / NW Urbandale Drive / Meredith Drive | Transportation Incident | Existing | URB CIP# ST06-03 | NEW | In progress | 2 |  |  | Funding/FHW A | Department of Engineering and Department of Public Works | Fed/State & local (Grimes) | Federal/State and TIF | 51000000 | Transportation issues, Safety, Improved access | 3 years+
| 100th Street Interchange at I-35/80 | Transportation Incident | Existing | URB CIP# ST06-11 | NEW | In progress | 2 |  |  | Funding/FHW A | Department of Engineering and Department of Public Works | FHWA/Johnston /State | Federal/State and TIF | 8750000 | Transportation issues, Safety, Improved access | 5 years
| Rocklyn Creek North of Urbandale Ave. | Flash Flooding | Existing | URB CIP# SS14-02 | New | Under development | 1 |  |  | Funding | Floodplain Manager | FEMA | Federal/State/GOB | 60000 | Reduce damage from flash flooding | 2 years
| Traffic Signal Battery Backup Program | Infrastructure Failure | Existing | URB CIP# TR14-01 | NEW | In progress | 1 |  |  | None Identified | Department of Engineering and DPW | Contiguous communities/ State | Federal/State/GOB | $79,000, | Back signals for traffic safety | This year

## Urbandale Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| NOAA Weather Radios at District Buildings | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | Building and Grounds | None Identified | General Funds | 1000 | Ensure information on watches and warnings issued is received by personnel at all bodings in district to take necessary measures to shelter students and staff and/or make decisions regarding modifications to dismissal | 1 Year
| Move Generator from Middle School to Jensen Elementary | Infrastructure Failure | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | None | Building and Grounds | None Identified | General Funds | 3500 | Provide back-up power in the event of outage | 1 Year

## WDM Schools
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Installation of FEMA compliant safe rooms/areas in nine elementary school buildings. | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | School Board | FEMA, IA HSEMD | Sales Tax Proceeds, PPEL, Grants | TBD (Project Designer) | Protect lives of students at school buildings | 5 Years
| Installation of FEMA compliant safe rooms/areas in two Jr. High buildings and one Freshman High School. | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | School Board | FEMA, IA HSEMD | Sales Tax Proceeds, PPEL, Grants | TBD (Project Designer) | Protect lives of students at school buildings | 5 Years
| Installation of generator(s) to serve the FEMA compliant safe rooms/areas in nine elementary buildings. | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | School Board | FEMA, IA HSEMD | Sales Tax Proceeds, PPEL, Grants | TBD (Project Designer) | Protect lives of students at school buildings | 5 Years
| Installation of generator (s) to serve the FEMA compliant safe rooms/areas in two Jr. High buildings and one Freshman High School. | Tornado | Existing | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | School Board | FEMA, IA HSEMD | Sales Tax Proceeds, PPEL, Grants | TBD (Project Designer) | Protect lives of students at school buildings | 5 Years

## West Des Moines
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Extending levee system at Raccoon River Park to Westerly City Boundaries | River Flooding | New | DPW Planning Analysis | Not Started / Continue |  | 4 |  |  | Cost | Department of Public Works | USACE, IDNR | City Bonds as match for Federal funds | $9.0 million | Flooding of industrial and residential properties | 6 Years
| Elevation of I-35 Bridge over Raccoon River and Highway 28 Bridge over Raccoon River to mitigate washout | River Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Cost | Iowa DOT | None | N/A | TBD by engineer | Closure of critical regional transportation route | 6 Years
| Pursue remedial flood mitigation actions associated with the Southeast Des Moines (SEDM) Levee, US 65 | River Flooding | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Cost | Iowa DOT, USACE and others TBD | None | PDM, HMGP | TBD | Closure of critical regional transportation route | TBD
| Lining of public sewers in the Valley Junction Area to mitigate infiltration at the Main Pump-2 Phases | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Cost, workload | Department of Public Works | EPA, IDNR | PDM, HMGP | $810,000 / Phase 1 $785,000 / Phase 2 | Property damage due to sewer backup. Capacity deficiencies at WWTP. | 1 Year
| Lining of public sewers in the Fairmeadows Creek Area to mitigate infiltration of the main pump | Flash Flooding | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Cost, workload | Department of Public Works | EPA, IDNR | PDM,HMGP | $2.3 million | Property damage due to sewer backup. Capacity deficiencies at WWTP. | 5 Years
| Construct safe room at City Hall for IT assets and infrastructure | Windstorms | Existing | Hazard Mitigation Plan | In Progress / Continue |  | 4 |  |  | Cost, existing infrastructure | Department of Public Works | IHSEMD, FEMA | General Funds | 90000 | Loss of critical local government database and communication devices, including citizen access | 5 Years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing and New | NFIP floodplain mgt. program | In Progress / Continue |  | 2 |  |  | None | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Potential property and life safety losses due to poor planning and flood water anticipation. | Ongoing

## Windsor Heights
Action ID (MPO Only) | Mitigation Project / Activity Description | Primary Hazard Addressed | Existing or New Structures | Planning / Implementation Mechanism | 2018 Action Status | 2018 Action Status Comment | Goal # | STAPLEE Score (MPO Only) | Priority (MPO Only) | Obstacles to Implementing | Responsible Office | Partners | Potential Funding Source | Cost Estimate | Benefits | Timeline
| Install residential check valves at Washington Avenue and 70th Street | Flash Flooding | Existing | Storm Water Management Plan | Not Started / Continue |  | 4 |  |  | Funding | Sanitary Sewer District | None Identified | Sewer Fund | $2,000 per home | Prevent water back-up in homes | 1 Year
| replace storm sewer intakes | Flash Flooding | Existing | Storm Water Management Plan | In Progress / Continue |  | 4 |  |  | None Identified | Department of Public Works | None identified | Stormwater Utility Fund | $5,000 per intake | Improves flow of runoff | 2 Years
| Harden City Hall to meet FEMA 361 Community Shelter Specifications | Windstorms | Existing | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Funding | Fire Department | None Identified | PDM, HMGP | TBD by engineer | Life safety, Regulatory | 5 Years
| Identify potential future shelter sites | Windstorms | Existing & New | Hazard Mitigation Plan | Not Started / Continue |  | 4 |  |  | Funding | Fire Department | None Identified | Department Salaries | <$250,000 | Life safety | 5 Years
| Continue to comply with the NFIP by enforcing floodplain management ordinance, including regulating/ monitoring new construction and substantial improvements in the SFHA; and participating in floodplain identification and mapping. | River Flooding | Existing & New | NFIP floodplain mgt. program | In Progress / Continue |  | 1 |  |  | None Identified | Floodplain Manager | IDNR, FEMA | Existing Resources | N/A | Regulatory, Prevents flooding and property loss | Ongoing
| Walnut Creek bank stabilization | River Flooding | Existing | Storm Water Management Plan | NEW |  | 4 |  |  | Access to property | DPW/ Engineering | FEMA/DPW/ Contractors | HMGP, WIRB Grant | TBD by engineer | Erosion, Property loss | Ongoing
| Saferoom at Colby Park and DPW | Tornado | New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | Department of Public Works | FEMA | HMGP | TBD by engineer | Life safety | 2 Years
| Install generator at Community and Events Center | Windstorms | New | Hazard Mitigation Plan | NEW |  | 4 |  |  | Funding | Department of Public Works | FEMA | HMGP | TBD by engineer | Life safety, Operational continuity | 2 Years